## till 20 (hidden)
Row Labels | Count of Type
Bug | 15
clarified | 16
Duplicate | 1
Enhancement | 18
Not required | 5
pending clarificaiton | 2
wip | 6
retest | 6
Grand Total | 69

## summarytill 24th (hidden)
Row Labels | Count of Type
Bug | 26 | bug fix and bounce module
clarified | 18
Duplicate | 1
Enhancement | 23
Not required | 7
WIP | 18 | july 1to 7 | GST, multiple vendors.
Pending clarification | 2
Grand Total | 95

## summary till 26th (hidden)
Row Labels | Count of Type
Bug | 33
clarified | 18
Duplicate | 1
Enhancement | 25
Not required | 7
Pending clarification | 2
retest | 2
WIP | 24
Grand Total | 112

## summary till 29th (hidden)
Row Labels | Count of Type
Bug | 31
Bug-fixed | 22
clarified | 22
Duplicate | 1
Enhancement | 29
Not required | 8
Pending clarification | 2
retest | 6
WIP | 24
(blank)
Grand Total | 145

## summary till 30th (hidden)
Row Labels | Count of Type
Bug | 13
Bug-fixed | 22
clarified | 25
Duplicate | 1
Enhancement | 30
Not required | 8
Pending clarification | 2
retest | 6
WIP | 28
(blank)
Bug fixed | 21
Grand Total | 156

## Summary (hidden)
Activites status |  | Daywise Pending report | [10 empty] | Bug Completed & Pending report
Activities / Type | Total | Date | Bug | Bug fixed | Clarified | Duplicate | Enhancement | Not required | Pending clarification | Retest | WIP | Grand Total | Date | Bug | Bug fixed | Grand Total
Bug | 27 | 2020-06-12 |  |  |  |  | 1 | 1 |  |  |  | 2 | 2020-06-15 | 1 | 5 | 6
AP Checker | 1 | 2020-06-15 | 1 | 5 | 5 | 1 | 14 | 5 |  |  | 1 | 32 | 2020-06-19 |  | 7 | 7
AP Invoice maker/ECF | 1 | 2020-06-16 |  |  | 4 |  | 2 | 1 |  |  | 4 | 11 | 2020-06-20 | 1 | 4 | 5
AP/Audit Maker | 1 | 2020-06-17 |  |  | 1 |  | 1 |  |  |  |  | 2 | 2020-06-22 |  | 2 | 2
Asset capitalization | 1 | 2020-06-18 | [6 empty] | 1 |  | 1 | 2 | 2020-06-23 |  | 1 | 1
Bounce/AP maker | 1 | 2020-06-19 |  | 7 | 4 |  | 1 |  | 1 |  | 3 | 16 | 2020-06-24 |  | 5 | 5
ECF | 7 | 2020-06-20 | 1 | 4 | 2 |  | 3 |  |  |  | 1 | 11 | 2020-06-25 |  | 5 | 5
Employee query | 1 | 2020-06-22 |  | 2 | [7 empty] | 2 | 2020-06-26 |  | 2 | 2
FA / GRN Approval | 1 | 2020-06-23 |  | 1 | 1 |  | 1 |  |  |  | 4 | 7 | 2020-06-27 | 10 |  | 10
FA / GRN Inward | 2 | 2020-06-24 |  | 5 | 1 | [5 empty] | 4 | 10 | 2020-06-29 |  | 10 | 10
FA / PO Template | 1 | 2020-06-25 |  | 5 |  |  | 1 |  |  | 1 | 1 | 8 | 2020-06-30 | 1 | 2 | 3
Inward | 1 | 2020-06-26 |  | 2 |  |  | 2 |  |  | 1 | 4 | 9 | 2020-07-03 | 9 |  | 9
Rent / Approval Summary | 2 | 2020-06-27 | 10 |  | 2 |  | 1 | 1 |  | 3 |  | 17 | 2020-07-04 | 1 |  | 1
Rent / Expense Create | 2 | 2020-06-29 |  | 10 | 2 |  | 2 |  |  | 1 | 1 | 16 | 2020-07-23 | 4 |  | 4
Rent / Expense GRN Approval | 2 | 2020-06-30 | 1 | 2 | 3 |  | 1 |  |  |  | 4 | 11 | Grand Total | 27 | 43 | 70
Rent / Property Summary | 1 | 2020-07-03 | 9 | [7 empty] | 2 | 11
Supplier management | 2 | 2020-07-04 | 1 | [7 empty] | 5 | 6
Bug fixed | 43 | 2020-07-23 | 4 | [7 empty] | 6 | 10
ALL Screen | 4 | Grand Total | 27 | 43 | 25 | 1 | 30 | 8 | 2 | 6 | 41 | 183
AP Invoice maker | 11
ECF | 13
Inward | 1
Maintenance | 1
Payment | 2
Supplier management | 11
Clarified | 25
ALL Screen | 1
AP approval summary | 1
AP Invoice maker | 14
ECF | 4
Inward | 2
Payment | 1
Supplier management | 2
Duplicate | 1
ECF | 1
Enhancement | 30
ALL Screen | 2
AP Invoice maker | 5
ECF | 11
Inward | 4
Maintenance | 2
Payment | 2
Supplier management | 4
Not required | 8
AP Invoice maker | 3
ECF | 1
Maintenance | 2
Payment | 2
Pending clarification | 2
ECF | 1
Master | 1
Retest | 6
Ammort | 1
AP Invoice maker | 1
ECF | 1
Supplier management | 3
WIP | 41
ALL Screen | 2
AP and ECF | 1
AP Invoice maker | 5
AP&ECF | 2
Asset capitalization | 1
Bounce/AP maker | 2
ECF | 11
FA | 3
FA / Document Inward | 1
FA / Invoice maker | 1
FA / PO Maker | 1
Maintenance | 4
Payment | 1
Paymode | 1
Reports | 4
Supplier management | 1
Grand Total | 183

## summary till 03rd july (hidden)
Row Labels | Count of Type
Bug | 26 | includes bug of Rent and FA
Bug fixed | 43
clarified | 25
Duplicate | 1
Enhancement | 30
Not required | 8
Pending clarification | 2
retest | 6
WIP | 36
(blank)
Grand Total | 177

## Pivot (hidden)
Count of Type |  | Count of Type | Column Labels
Date | Total | Date | Bug | Bug fixed | Grand Total
Bug | 27 | 2020-06-15 | 1 | 5 | 6
AP Checker | 1 | 2020-06-19 |  | 7 | 7
AP Invoice maker/ECF | 1 | 2020-06-20 | 1 | 4 | 5
AP/Audit Maker | 1 | 2020-06-22 |  | 2 | 2
Asset capitalization | 1 | 2020-06-23 |  | 1 | 1
Bounce/AP maker | 1 | 2020-06-24 |  | 5 | 5
ECF | 7 | 2020-06-25 |  | 5 | 5
Employee query | 1 | 2020-06-26 |  | 2 | 2
FA / GRN Approval | 1 | 2020-06-27 | 10 |  | 10
FA / GRN Inward | 2 | 2020-06-29 |  | 10 | 10
FA / PO Template | 1 | 2020-06-30 | 1 | 2 | 3
Inward | 1 | 2020-07-03 | 9 |  | 9
Rent / Approval Summary | 2 | 2020-07-04 | 1 |  | 1
Rent / Expense Create | 2 | 2020-07-23 | 4 |  | 4
Rent / Expense GRN Approval | 2 | Grand Total | 27 | 43 | 70
Rent / Property Summary | 1
Supplier management | 2
Bug fixed | 43
ALL Screen | 4
AP Invoice maker | 11
ECF | 13
Inward | 1
Maintenance | 1
Payment | 2
Supplier management | 11
Clarified | 25
ALL Screen | 1
AP approval summary | 1
AP Invoice maker | 14
ECF | 4
Inward | 2
Payment | 1
Supplier management | 2
Duplicate | 1
ECF | 1
Enhancement | 30
ALL Screen | 2
AP Invoice maker | 5
ECF | 11
Inward | 4
Maintenance | 2
Payment | 2
Supplier management | 4
Not required | 8
AP Invoice maker | 3
ECF | 1
Maintenance | 2
Payment | 2
Pending clarification | 2
ECF | 1
Master | 1
Retest | 6
Ammort | 1
AP Invoice maker | 1
ECF | 1
Supplier management | 3
WIP | 41
ALL Screen | 2
AP and ECF | 1
AP Invoice maker | 5
AP&ECF | 2
Asset capitalization | 1
Bounce/AP maker | 2
ECF | 11
FA | 3
FA / Document Inward | 1
FA / Invoice maker | 1
FA / PO Maker | 1
Maintenance | 4
Payment | 1
Paymode | 1
Reports | 4
Supplier management | 1
Grand Total | 183

## Pivot 1
Count of Type | Column Labels
Row Labels | Done | Duplicate | Next phase | Not required | Report generation | To be discussed | To be taken up for dev | To be tested | (blank) | Grand Total
Accounting entry | [6 empty] | 1 |  |  | 1
Bug | 6 | 1 |  |  |  |  | 9 |  |  | 16
Bug fixed |  |  |  | 63 | [5 empty] | 63
Clarified |  |  |  | 25 | [5 empty] | 25
Data migration |  |  |  | 1 | [5 empty] | 1
Duplicate |  |  |  | 6 | [5 empty] | 6
Enhancement | 2 | 2 | 10 | 3 | 1 | 7 | 64 |  |  | 89
Failed Bugs | [6 empty] | 2 | 1 |  | 3
Maintenance | [6 empty] | 1 |  |  | 1
Not required | 1 |  |  | 9 | [5 empty] | 10
Pending clarification | 1 | [8 empty] | 1
Report | [6 empty] | 1 |  |  | 1
Retest | 3 | [6 empty] | 1 |  | 4
To be done | [6 empty] | 1 |  |  | 1
WIP | 6 | 2 |  | 1 | 2 | 5 | 22 | 1 |  | 39
(blank)
Grand Total | 19 | 5 | 10 | 108 | 3 | 12 | 101 | 3 |  | 261

## Pivot 2
Count of Sai's Comments - 31st Jul | Column Labels
Row Labels | High | Low | Medium | (blank) | Grand Total
Done |  |  |  | 19 | 19
Duplicate |  |  |  | 5 | 5
Next phase | 3 |  | 7 |  | 10
Not required |  |  |  | 108 | 108
Report generation | 3 |  |  |  | 3
To be discussed |  |  |  | 12 | 12
To be taken up for dev | 66 | 4 | 31 |  | 101
To be tested |  |  |  | 3 | 3
(blank)
Grand Total | 72 | 4 | 38 | 147 | 261

## Updated Summary
Summary of Action items - Except for Rental & SMS module points
Status | High | Low | Medium | NA | Grand Total
Done |  |  |  | 19 | 19
Duplicate |  |  |  | 5 | 5
Next phase | 3 |  | 7 |  | 10
Not required |  |  |  | 108 | 108
Report generation | 3 |  |  |  | 3
To be discussed |  |  |  | 12 | 12
To be taken up for dev | 66 | 4 | 31 |  | 101
To be tested |  |  |  | 3 | 3
(blank)
Grand Total | 72 | 4 | 38 | 147 | 261

## Pre-Prod Testing Team
# | Date |  | Activity/Module | Issue Description | Person Responsible | Testing team comments | Type | Sai's Comments - 31st Jul | Priority | Tech team Target date | order | target date by tech | Bug fixed date
1 | 2020-06-12 |  | AP | Dedupe check for vendor claims should be mandatory at AP | Gayathri | Already communicated to tech | Enhancement | Done |  |  | Maruthi | enhancement
2 | 2020-06-15 |  | Bounce/AP maker | Rejected Claims_ Entry got vanished and unable to find the document anywhere in the system. NPO2006130013 - rejected from Invoice maker, the transaction vanished - unable ,NPO2006130016 | Santhanam | Bounce-reject moulde to be checked | WIP | Done |  | 2020-06-21 | Maruthi | 2 days
3 | 2020-06-16 |  | Inward | Inward Screen _ Document Type _ Able to select only for the invoice option | Gayathri | Currently only Invoice avlb | Enhancement | Done
4 | 2020-06-18 |  | ECF | If the claim raised by CO for various branch, we require this option to proceed further | Gayathri | Testing team to check ECF CO-GST dropdpwn option to be given | WIP | Done
5 | 2020-06-19 |  | ECF | ECF - If we are the raiser of the claim instead of Bank (mumbai) and our state (tamilnadu)is different from the invoice means, the gst part will be obviously showing as IGST instead of cgst and sgst. | Vimala | To be confifmed with SK | Pending clarification | Done
6 | 2020-06-19 |  | ECF | ECF - if AP maker rejects an ecf, the rejected ECF will not comes in ecf maker queue | Vimala | Bounce option works-flow to be completed | WIP | Done |  |  | Maruthi
7 | 2020-06-20 |  | Supplier management | Branch level TDS- currently asking branch level tds |  | Branch level TDS | Bug | Done |  |  | Bug | 26th EOD
8 | 2020-06-23 |  | AP Invoice maker | NPO2006230027 - Payment processed without bank account number and beneficiary name, payment is in prepare payment queue | Preprod | clarified | WIP | Done
9 | 2020-06-25 |  | Payment | Prepare Payment - PPX cases are not allowed for netting, error as "Invalid Invoice Type". | Preprod | To be discussed with Maruthi | Not required | Done
10 | 2020-06-27 |  | Supplier management | Bank Account detail are available in Supplier Summary, but the account details shown as NA while raising an ECF | Preprod | Need to check | Retest | Done
11 | 2020-06-27 |  | Supplier management | Supplier Creation __in unreg vendor creation, when we enter tax details , system doesn't allows to submit as it says"Pls enter Tax.no". What does Tax.no means? | Preprod | Need to check | Retest | Done
12 | 2020-06-29 |  | ECF | IMPREST_ SUPPLIER NAME NOT AVAILABLE AND UNABLE TO CHOOSE THE SUPPLIER | Preprod | will check later once confirmation recd from tech support | Retest | Done
13 | 2020-06-30 |  | ECF | ECF Approval Summary - Approval button removed from the main summary page hence multiple selection option is not required. |  | Select all option to be removed | WIP | Done
14 | 2020-07-23 |  | FA / GRN Approval | GRN Approval: Bug- PO wise details are not available. | FA |  | Bug | Done
15 | 2020-07-23 |  | FA / GRN Inward | supplier name in this screen is given mandatory- only PO number is required not supplier name | FA |  | Bug | Done
16 | 2020-07-04 |  | Paymode | EFT paymode | Testing team |  | WIP | Done
17 | 2020-07-07 |  | Supplier management | Unable to mark vendor as inactive in supplier mgmt-error in header level |  |  | Bug | Done
18 | 2020-07-13 |  | PR | MEP numbers to be displayed as a drop down in PR maker screen for selecting the relevant PR. | KVB req |  | Bug | Done
19 | 2020-06-24 |  | Payment | Prepare Payment - Option Bulk or Netting option is not working properly | Preprod | To be discussed with Maruthi | Bug | Duplicate
20 | 2020-06-26 |  | Bounce/AP maker | If vendor is inactive-pipeline claims vanish now. Instead they should go to bounce queue | Testing team | It should not allow to submit the claim | WIP | Duplicate
21 | 2020-06-15 |  | AP Invoice maker | Clarification Request for cancel and reprocess cases -Payment cancellation and reprocessing | Gayathri | Payment reversal through system not available-can be done through JV | Enhancement | Next phase | High | Next Phase
22 | 2020-06-15 |  | ECF | For PPX claim TLD should be mandatory ( target liquidation date) to liquidate the amount on time from the supplier | Gayathri | Not a showstopper, can be taken as an enhancement later | Enhancement | Next phase | Medium | Next Phase
23 | 2020-06-20 |  | Supplier management | at the time of supplier creation, if actual spend was given wrongly as other than "0", then is there any popup shows that the actual should be 0 or if system allow us to proceed, then how the invoice amount cumulated after every utilization.-can we make this as non mandaory now | Vimala | Enhancement | Enhancement | Next phase | Medium |  | Maruthi | enhancement
24 | 2020-06-20 |  | Supplier management | supplier management query should be viewable for all at both sides, EMC and kvb | Vimala | name and id tagging | Enhancement | Next phase | Medium |  | Maruthi | name and id tagging in status -enhancment
25 | 2020-06-15 |  | ECF | option Request for Add invoice for the same vendor for the different expense month | Gayathri |  | Enhancement | Next phase | Medium
26 | 2020-06-15 |  | Maintenance | Tray Wise Document detail request for work Allotment | Gayathri |  | Enhancement | Next phase | Medium
27 | 2020-06-23 |  | ECF | Draft Mode reqd in ECF | Preprod | Enhancement | Enhancement | Next phase | High
28 | 2020-06-26 |  | Inward | Check box is required to separate the duplicate invoice at inward level | preprod | To be discussed with Maruthi | Enhancement | Next phase | Medium
29 | 2020-06-29 |  | ECF | Once the claim got moved to approver end the option given to Reject / Resend , but again the same claim unable to submit for approver after done the correction | Preprod | Enhancement | Enhancement | Next phase | High
30 | 2020-07-17 |  | ECF | ECF - Request from KVB - Required delete option in ECF Inventory. | Preprod |  | Enhancement | Next phase | Medium
31 | 2020-06-27 |  | Supplier management | If a vendor is not mapped with DD, but a payment needs to be sent thru DD as exception , in such case do we have an option of adding DD details in Credit line-vendors without account details are to be maintained with DD paymode option | Preprod | Not required | Not required | Not required
32 | 2020-06-29 |  | Supplier management | DD option request for all the vendors while upload through supplier query | Preprod | Need to check | Data migration | Not required
33 | 2020-06-30 |  | ECF | Vendor Name not showing in IMPREST ECF Claim Form (Vendor name / |  | To be discussed with Maruthi | WIP | Not required
34 | 2020-06-16 |  | Reports | How to generate the credit and debit report | Gayathri | Reports-collate in excel | WIP | Report generation | High | To be prioritized | Maruthi | format to be shared
35 | 2020-06-16 |  | Reports | How can we get the inward volume based on Query Screen then we require the Export excel option to work allotment | Gayathri | Reports-collate in excel | WIP | Report generation | High | To be prioritized | Maruthi | format to be shared
36 | 2020-07-15 |  | PPX | Vendor details and date details for Outstanding Capital advances "Details of advances paid" | Vignesh Selvaraj |  | Enhancement | Report generation | High
37 | 2020-06-15 |  | ECF | ECF resend option request from the approver end to attach the document at raiser level | Gayathri | Not a showstopper, can be taken as an enhancement later | Enhancement | To be discussed |  | Next Phase
38 | 2020-06-15 |  | ECF | ECF inventroy_ Claim edit option request -before approval | Vimala | Not a showstopper, can be taken as an enhancement later | Enhancement | To be discussed |  | Next Phase | Maruthi | enhancement
39 | 2020-06-17 |  | ECF | Query screen request - Branch level/DO level query screen and Overall query screen for EMC and CO to be developed separately. | Gayathri | To be discussed with Maruthi | Enhancement | To be discussed |  | To be prioritized | Maruthi | ECF inventory screen available-to be enhanced
40 | 2020-06-19 |  | AP | Sample Request for DD paymode with beneficiary name for testing purpose. Payment through Credit GL and DD to be checked for Mid cash sus hit | Gayathri | To be discussed with Maruthi-GL to be maintained | WIP | To be discussed |  |  | Maruthi | mapping GL will be provided
41 | 2020-06-20 |  | Maintenance | Approver redelegation option required | Gayathri |  | Enhancement | To be discussed
42 | 2020-07-23 |  | FA / Invoice maker | 1. Invoice maker: Chances of missing TDS deductions are higher. Possible solutions- | FA |  | WIP | To be discussed
43 | 2020-07-23 |  | FA | a) Intimation to check | FA |  | WIP | To be discussed
44 | 2020-07-23 |  | FA | b) 194Z | FA |  | WIP | To be discussed
45 | 2020-07-23 |  | FA | 1. Asset maker: Not restricted to populate specific category of invoices. | FA |  | WIP | To be discussed
46 | 2020-06-15 | ATMA | Supplier management | Pls change the Pop up message for already exist vendor /PAN | Gayathri | Text to be changed | Enhancement | To be taken up for dev | Low | 2020-06-21
47 | 2020-06-15 | AP | AP Invoice maker | View Transaction Details is not updated yet in Maker Screen. The remarks given by multiple approvers to be captured properly in the view transacton details tab. | Gayathri | Records avaialble from AP- Required from ECF raiser -approver details.Its not a showstopper enhancement - Maker name should be shown | Enhancement | To be taken up for dev | High | Next Phase
48 | 2020-06-15 | AP | Payment | unable to select the multiple transaction for prepare for payment at a single instance. Bulk option not working | Gayathri | Not a showstopper, can be taken as an enhancement later | Enhancement | To be taken up for dev | Medium | Next Phase
49 | 2020-06-15 | AP | AP Invoice maker | Duplicate claim should be shown in the inprocess level not only for the approved ECFs. | Gayathri | Enhancement | Enhancement | To be taken up for dev | Low
50 | 2020-06-15 | AP | ECF | ECF number rquest in all the screen | Sankari | To check with Maruthi for implementation | Enhancement | To be taken up for dev | Low | Next Phase | Maruthi | Before monthend
51 | 2020-06-15 | AP | ALL Screen | Date range , branch filter is unavailable in the query screen.-invoice maker summary | Santhanam | WIP- Required reports can be collated in an excel and forwarded to tech for development | Enhancement | To be taken up for dev | Low | Next Phase | Maruthi | Before monthend
52 | 2020-06-16 | REP AP | Reports | In bounce Summary Date Range Option Request | Gayathri | Reports-collate in excel | WIP | To be taken up for dev | Medium | To be prioritized | Maruthi | format to be shared
53 | 2020-06-16 | REP AP | Reports | Bounce and Reject Summary Export Excel option Require | Gayathri | Reports-collate in excel | WIP | To be taken up for dev | Medium | To be prioritized | Maruthi | format to be shared
54 | 2020-06-16 | AP | ALL Screen | Pls clarify how to clasify the CO payments while processing -branch filer in invoice maker. Filter to be given for Branch code, Date range and Raiser name | Gayathri | Branch level filter option to be given in Audit invoice maker screen | Enhancement | To be taken up for dev | High | To be prioritized | Maruthi
55 | 2020-06-18 | AP | Master | Receiver GST number to be given as drop down in ECF and AP end irrespective of the branch code selected | Gayathri | To be discussed with SK | Enhancement | To be taken up for dev | Medium
56 | 2020-06-19 | AP | ECF | ECF - in credit line, if we split payment mode in to 2, neft and DD, the amount allocation (Automatic amount to be picked up during paymode split) | Vimala | To be discussed with Maruthi | Enhancement | To be taken up for dev | High |  | Maruthi | enhancement
57 | 2020-06-15 | AP | Inward | AWB search option request for Query Screen and Inward Screen | Gayathri |  | Enhancement | To be taken up for dev | Medium
58 | 2020-06-20 | AP | Maintenance | Multiple E Mail option for rejection | Nanda |  | WIP | To be taken up for dev | Medium
59 | 2020-06-23 | AP | ECF | TDS capture in PPX and add row option in AP screen | Deen |  | WIP | To be taken up for dev | High
60 | 2020-06-23 | AP | AP Invoice maker | TDS rounding off -higher side-now doing on the lower side | Deen |  | WIP | To be taken up for dev | High
61 | 2020-06-23 | AP | ECF | Duplicate check should be at ECF Inventory level | Preprod | WIP | WIP | To be taken up for dev | High
62 | 2020-06-24 | AP | AP Invoice maker | For inactive vendors -claims in pipeline should not get processed in AP. It should get blocked before Authoriser level | Preprod | Enhancement | WIP | To be taken up for dev | Medium
63 | 2020-06-24 | AP | AP&ECF | Rounding off field to be given in debit entry screen and this amount should get adjusted in expense line on posting accounting entries | Testing team | WIP | WIP | To be taken up for dev | High
64 | 2020-06-24 | AP | AP&ECF | Other adjustment- field to be provided in debit screen to post discount after GST | Testing team | WIP | WIP | To be taken up for dev | High
65 | 2020-06-25 | AP | ECF | ECF - System should not allow to download ECF PDF before final approval | Preprod | Inward should not happen without the claim being approved by the final approver as per delmat | WIP | To be taken up for dev | High
66 | 2020-06-26 | AP | Inward | Inward Partial - While closing partially inwarded case screen automatically moves to the audit maker level. Total invoice received and processed should get tally at inward level. |  | Partial inward not be allowed, no. of documents should match with the inward count for invoices + other docs | Enhancement | To be taken up for dev | High
67 | 2020-06-26 | AP | AP Invoice maker | AP Invoice Entry - Bank details are not visible, to view the same we need to select the account number again. | preprod | retest | Bug | To be taken up for dev | High
68 | 2020-06-26 | AP | AP Invoice maker | Remove reject buttion from audit-checklist screen. Only bounce key is required | Testing team |  | WIP | To be taken up for dev | Medium
69 | 2020-06-26 | AP | ALL Screen | While entering invoice date system throws popup as "Your Selected Date Is Lessthen 6 Months" | Testing team | Text to be changed to " invoice date is greater than six months" | WIP | To be taken up for dev | High
70 | 2020-06-26 | AP | ECF | If vendor is inactive in ECF raiser module a popup can be given as "vendor inactive" while choosing the supplier | Testing team | Popup msg to be given as 'Vendor in Inactive status' | Bug | To be taken up for dev | Medium
71 | 2020-06-27 | Ammort | Ammort | Issue in Amort processing. To be checked in amort schedule screen and for Amort run | Preprod | Amort option avlb | Bug | To be taken up for dev | High
72 | 2020-06-27 | AP | ECF | While sending the ECF from checker to audit maker for re-audit, the data input done by the audit maker is not available instead the data from the ECF raiser end is available. | Preprod | Bug-AP after ist edit by maker, checker rejects again, the maker cannot see the edited data | Bug | To be taken up for dev | High
73 | 2020-06-29 | AP | ECF | Remarks / Description Should be Mandatory at Inventory level | Preprod | should be made mandatory at Raiser end | Enhancement | To be taken up for dev | High
74 | 2020-06-30 | AP | ECF | Inventory Screen_While raising PPX ECF, first choose as supplier payment select the supplier name as well suddenly or inbetween when I change the payment type for employee without submit the claim, the vendor name will appear for employee advance. |  | Bug | Bug | To be taken up for dev | High
75 | 2020-06-30 | AP | ECF | ECF / AP - System allows to raise claim for the vendor which is in Draft (Aproved vendor edited through modification request and pending for approvals) status. |  | To stop before authorisation level. Should not allow raiser to raise the claim if the vendor is in modification mode | WIP | To be taken up for dev | High
76 | 2020-06-30 | AP | AP Invoice maker | Cat - Sub Cat required in detailed format at AP Screen |  | To be discussed with Maruthi | Maintenance | To be taken up for dev | High
77 | 2020-06-30 | AP | ALL Screen | Transaction History required in query screen |  | Enhancement | WIP | To be taken up for dev | Medium
78 | 2020-07-23 | FA | FA / PO Maker | PO Maker: There is no option for entering delivery details | FA |  | WIP | To be taken up for dev | High
79 | 2020-07-23 |  | FA / GRN Inward | GRN Inwards: Manual entry of asset details is critical. Whereas the provision for the same is not available | FA |  | Bug | done
80 | 2020-07-23 | FA | FA / Document Inward | Document inwards: There is no check between PO amount and invoice amount. Whereas the auto fetching option is available in ECF. Proper error msg to be displayed in case of a mismatch against PO in details entered while inward | FA | Bug | Bug | To be taken up for dev | High
81 | 2020-07-03 | AP | ECF | Special character in Purpose field | Testing team | bug | WIP | To be taken up for dev | Medium
82 | 2020-07-03 | AP | AP and ECF | Need 'Rounding off' option in Debit Tab for the amount variation | Testing team |  | WIP | To be taken up for dev | High
83 | 2020-07-03 | AP | ECF | Remarks Field with Word count: Now system allow the word counts total - 255 but does not allow to submit | Testing team |  | Bug | To be taken up for dev | Medium
84 | 2020-07-04 | FA | Asset capitalization | Accounting entry post capitalization not given | Testing team |  | Accounting entry | To be taken up for dev | High
85 | 2020-07-07 | ATMA | Supplier management | In supplier creation _ unable to decrease the branch code count post updation of profile branch |  | Failed_system allow to modify the deactivate /terminate vendor-allows to modify even in inactive status without changing to active | Failed Bugs | To be taken up for dev | Medium
86 | 2020-07-07 | AP | AP | AP _ unable to process the ECF with discount and other deductions-discount not working |  | Failed-if we enter 3 and input one record and want to modity branch code unable to change | Failed Bugs | To be taken up for dev | High
87 | 2020-07-11 | TA | TA | TA module on behalf of option to be given | KVB req |  | Enhancement | To be taken up for dev | High
88 | 2020-07-11 | PO | PO | PO cover note | KVB req |  | WIP | To be taken up for dev | High
89 | 2020-07-11 | FA | FA | FA clearing should show all entries - even the entries routed thorugh JV module | KVB req |  | Enhancement | To be taken up for dev | Medium
90 | 2020-07-11 | PO | GRN | option to input installation date for selected commodities-button with Y or N flag | KVB req |  | WIP | To be taken up for dev | High
91 | 2020-07-11 | PO | PR | Capitalization buttion in PR checker | KVB req |  | WIP | To be taken up for dev | High
92 | 2020-07-11 |  | PPX-advance | Purpose given at the time of booking advance has to be shown against advance no on liquidation along with branch code-raiser | KVB req |  | WIP | Duplicate
93 | 2020-07-11 | AP | PPX - PO | PO number to be captured in advance booking | KVB req |  | WIP | To be taken up for dev | High
94 | 2020-07-11 | AP | ECF-AP | Only expense GL to be shown in debit screen for revenue expense items, currently its showing assets GLs also | KVB req | validation to be built | WIP | To be taken up for dev | High
95 | 2020-07-14 | AP | Claim forms & AP | Expense GL description to be displayed in Claim forms and in AP for clarity | KVB req |  | Enhancement | To be taken up for dev | High
96 | 2020-07-13 | AP | AP - Claims | Option to select retention GL and its release from AP - to be discussed | KVB req | Retention release to be discussed | Enhancement | To be taken up for dev | High
97 | 2020-07-13 | AP | AP - Claims | Recommendation note/approval note - Need to create a note format while raising claim. | KVB req | Memo field to include approval note | Enhancement | To be taken up for dev | High
98 | 2020-07-13 | PO | PR | PR creation - option for the PR checker to reject and send back to PR Maker for amendment | KVB req |  | Enhancement | To be taken up for dev | High
99 | 2020-07-13 | PO | PO | PO format to be changed as per their requirement - Format provided | KVB req |  | Enhancement | To be taken up for dev | High
100 | 2020-07-13 | PO | PO | Asset ID logic to be checked from IT - to check feasibility on changing the Asset ID logic | KVB req |  | Enhancement | To be taken up for dev | High
101 | 2020-07-13 |  | PO | Asset maunfacturer data to fetch from PO | KVB req |  | Enhancement | Duplicate
102 | 2020-07-13 | PO | PO | Installation flag, warranty start date, end date to be captured in GRN | KVB req |  | Enhancement | To be taken up for dev | High
103 | 2020-07-13 | PO | PO | installation date will be warranty start date | KVB req |  | Enhancement | To be taken up for dev | High
104 | 2020-07-13 | PO | PO | warranty period to fetch in PO | KVB req |  | Enhancement | To be taken up for dev | High
105 | 2020-07-13 |  | PO | Optional Flag in PO maker to mark for capitalization defaulting the AP check-box for Capitalisation flag (Still AP can over-ride based on the cover note given) | KVB req | This is handled at the PR level | Enhancement | Not required
106 | 2020-07-13 | TA | TA / AP | Expense GL with cat and subcat handoff from TA to AP for TCF | Sai Anand/Rajesh | Clarification with SK on history emp master data for grade change | Enhancement | To be taken up for dev | High
107 | 2020-07-13 | TA | TA / AP | Multiple vendor with GST details from TA to be routed into AP through the latest Employee claim form framework | Sai Anand/Rajesh |  | Enhancement | To be taken up for dev | High
108 | 2020-07-13 | TA | TA / AP | Reverse feed from AP to TA for recording changes if any | Sai Anand/Rajesh | Clarification from SK on reverse feed | Enhancement | To be taken up for dev | High
109 | 2020-07-13 | AP | AP | Checklist in Audit Maker - options to be changed as 'OK', 'NOT OK' & 'NA' | Sai Anand |  | Enhancement | To be taken up for dev | medium
110 | 2020-07-13 | FA | FA | In FA asset maker - Separate tabs for Regular, CWIP & BUC. First 2 are already available, BUC to be included. The txn flow should be based on the debit GL input in AP module. FA Clearing/CWIP/BUC are the three GL options for FA in AP module for selection | Sai Anand |  | Enhancement | To be taken up for dev | High
111 | 2020-07-21 |  | ATMA | Removal of RM approval: Vendor Management being held by EMC, RM approval would be time consuming. Hence RM approval should be removed for vendor creation and modification. | Sai Anand | Need not remove RM level, can be handled internally at EMC. | Enhancement | Not required
112 | 2020-07-21 | PO | GRN | GRIN module to caputure installation date and warranty details. Installation required - Yes or No to be included in the GRN module. | KVB req |  | Enhancement | To be taken up for dev | High
113 | 2020-07-15 | AP | PPX | PPX has the purpose field in the PPX maker screen but that is not displayed in AP. it is required to be displayed in AP to identify which is to be liquidated. | Vignesh Selvaraj |  | Enhancement | To be taken up for dev | High
114 | 2020-07-15 | AP | PPX | For PO - linked PPX, there needs to be an input field to capture PO number against which advance is given. for that, the flow shall be PO creation, in PPX request after selection of vendor PO dropdown box (non-mandatory field) listing all POs against the vendor. | Vignesh Selvaraj |  | Enhancement | To be taken up for dev | High
115 | 2020-07-15 |  | PR PO | Flag in PR maker to mark for capitalization defaulting the AP check-box for Capitalisation flag (Still AP can over-ride based on the cover note given) | Vignesh Selvaraj |  | Enhancement | Duplicate
116 | 2020-07-15 | AP | AP | Hardcoding for transactions marked for capitalization to be Removed. Along with all expenses WiseFin GLs, additionally 3 WiseFin GL to be listed in Drop-down viz - 390100, 390101, and 390102. FA clg-Regular, BUC & CWIP | Vignesh Selvaraj |  | Enhancement | To be taken up for dev | High
117 | 2020-07-15 | AP | AP | FA Clearing shall list all transactions (Regular, BUC & CWIP shall restrict vouchers in 390100, 390101, and 390102. | Vignesh Selvaraj |  | Enhancement | To be taken up for dev | High
118 | 2020-07-15 | FA | FA | Restrict txns of 390101 to flow to 307 and 370. (Own and Leased Bldg Asset GL categories) | Vignesh Selvaraj |  | Enhancement | To be taken up for dev | High
119 | 2020-07-15 | AP | PPX | PPX Maker shall have a drop down for Vendor Capital Advance, Vendor Revenue advance, Employee advance & Deposits. If the PO selected is marked for capitalisation, then FA advance GL to be defaulted in the debit line. | Vignesh Selvaraj |  | Enhancement | To be taken up for dev | High
120 | 2020-07-15 |  | PPX | PPX is to be used only for payment to suppliers, not for employees. Advance for employees is only in TA Module. (refer "advance accounting" sheet in "Temporary accounting flow for Go-live" file sent previously). | Vignesh Selvaraj |  | Enhancement | Not required
121 | 2020-07-15 | AP | PPX | All PPX to be renamed to "Advances" | Vignesh Selvaraj |  | Enhancement | To be taken up for dev | High
122 | 2020-07-15 | AP | AP | Additional Tax type in Tax Master table for GST namely CGST - FA, SGST - FA, and IGST - FA. | Vignesh Selvaraj |  | Enhancement | To be taken up for dev | High
123 | 2020-07-15 | AP | ECF/ AP | GST field shall have a drop drown between normal (existing) and GST - FA. | Vignesh Selvaraj |  | Enhancement | To be taken up for dev | High
124 | 2020-07-15 |  | Paymode | Use 275300110 GL for mapping pay modes - PPX Supplier, NEFT, DD, Cheque, WiseFin Suspense. - Update in Pay-mode Master / Table. | Vignesh Selvaraj |  | Enhancement | To be discussed
125 | 2020-07-15 | FA | FA | FA Asset Maker should Have 3 Tabs - Regular, CWIP, BUC. | Vignesh Selvaraj |  | Enhancement | To be taken up for dev | High
126 | 2020-07-15 | PO | FA / PO | Asset ID generation to skip for products where Expense Type = Service, during PO | Vignesh Selvaraj |  | Enhancement | To be taken up for dev | High
127 | 2020-07-15 | PO | FA / PO | Asset ID generation to skip for Asset Cat Own bldg and Leased bldg(cat Code 307, 370) during PO | Vignesh Selvaraj |  | Enhancement | To be taken up for dev | High
128 | 2020-07-15 | PO | FA / PO | Asset ID generation to skip for Asset GL 302111 - IT Equipment - Spares during PO | Vignesh Selvaraj |  | Enhancement | To be taken up for dev | High
129 | 2020-07-15 |  | FA | Asset Merger to be modified not to create new asset ID instead we shall club the values and audit trail to the parent asset (choice of an asset to be made available). i.e., currently, we have A+B = C, instead, we need A + B = A. | Vignesh Selvaraj |  | Enhancement | To be discussed
130 | 2020-07-15 | FA | FA / AP | Accounting entries given to be updated | Vignesh Selvaraj |  | Enhancement | To be taken up for dev | High
131 | 2020-07-15 | FA | FA | Depreciation to be calculated based on Assets transaction details & the respective put to use date instead of Asset Summary. Txn ID = Asset ID(16 digit)/no of capitalisation(2 digit)/Txn running number(2 digit) | Vignesh Selvaraj |  | Enhancement | To be taken up for dev | High
132 | 2020-07-15 | FA | FA | Insertion of "Asset ID" field in Property Master | Vignesh Selvaraj |  | Enhancement | To be taken up for dev | medium
133 | 2020-07-15 | FA | FA | Input field for capturing Property ID while capitalizing Asset from BUC Tab - FA Maker (Mandatory) | Vignesh Selvaraj |  | Enhancement | To be taken up for dev | medium
134 | 2020-07-21 | FA | FA | Restriction on Put-to-use Date for Cap date Change - beginning of current Financial Year. Any change should be done in the current FY | KVB req |  | Enhancement | To be taken up for dev | High
135 | 2020-07-21 | PO | PAR MEP | Memo note option in MEP and PAR | KVB req |  | Enhancement | To be taken up for dev | High
136 | 2020-07-21 | PO | PAR MEP | PAR MEP utilisation, Bursting and hierachy to be modified as given in mail dt - 20th July 2020. | Vignesh Selvaraj |  | Enhancement | To be taken up for dev | High
137 | 2020-07-21 | PO | PAR MEP | Burst option upto 10% | KVB req |  | Enhancement | To be taken up for dev | Medium
138 | 2020-07-21 | PO | PAR MEP | MEP amendment upto 25%. | KVB req |  | Enhancement | To be taken up for dev | Medium
139 | 2020-07-21 | PO | PAR MEP | MEP date extension - to be done within FY | KVB req |  | Enhancement | To be taken up for dev | High
140 | 2020-07-21 | AP | PPX | De-dupe option to be disabled in Advance Maker. Audit checklist & View txn not available in PPX screen | Malathy R |  | Enhancement | To be taken up for dev | High
141 | 2020-07-21 | SMS | SMS | AMC should allow pre-dated entry | KVB req |  | Enhancement | To be taken up for dev | Medium
142 | 2020-07-21 | SMS | SMS | Search assets by DO (multiple branches under 1 DO) in AMC maker | KVB req |  | Enhancement | To be taken up for dev | Medium
143 | 2020-07-21 | SMS | SMS | Vendor interface for tickets in SMS module. | KVB req |  | Enhancement | To be taken up for dev | Medium
144 | 2020-07-21 | AP | ECF/AP | Cat, subcat and GL description to be displayed below the respective fields | KVB req |  | Enhancement | To be taken up for dev | Medium
145 | 2020-07-21 | AP | ECF/AP | Validation between GST applicability tick/untick against the variation in the inv amt and taxable amount input | KVB req |  | Enhancement | To be taken up for dev | Medium
146 | 2020-07-22 | ATMA | Supplier management | Supplier Management - Profile Contract - Space is not allowed in all the tabs. | Preprod |  | Enhancement | To be taken up for dev | Medium
147 | 2020-07-22 | ATMA | Supplier management | Supplier Management - Deactivated / Terminated vendor is not getting reflect in Supplier Management Query screen (In SIT). | Preprod |  | Enhancement | To be taken up for dev | Medium
148 | 2020-07-01 | AP | PPX | PPX - GST applicable option is not required (Remove GST Check box). | Preprod |  | WIP | To be taken up for dev | Medium
149 | 2020-07-17 | AP | AP | AP - The maker chose "amort" at maker level. However checker doesn't have the option to see whether amort has selected on the transaction. | Preprod |  | Bug | To be taken up for dev | Medium
150 | 2020-07-22 | AP | AP | Ammort to be renamed as Prepaid Expenses | KVB req |  | Enhancement | To be taken up for dev | Medium
151 | 2020-07-22 | PO | PAR MEP | PAR and MEP selection - Description to be displayed | KVB req |  | Enhancement | To be taken up for dev | Medium
152 | 2020-06-19 |  | ECF | ECF - BSNL payment processed with Credit GL and got struck at AP final approval level. | Sudhakar | Credit GL input to be checked again | WIP | To be tested
153 | 2020-06-25 |  | Supplier management | In Supplier Mngt Deactivate screen status of the vendor shows as "Approved", however in the supplier management summary the same vendor is in "Draft" mode. Hence system throws an error while deactivating this vendor. | Preprod | Clarified-to be tested again | Retest | To be tested
154 | 2020-07-07 |  | ECF | ECF - For the vendor, paymode changed from NEFT and updated as DD, however while raising claims in ECF system shows the NEFT details instead of DD |  | Failed | Failed Bugs | To be tested
155 | 2020-07-07 | AP | ECF | ECF / AP - Unable to process the request along with TDS Exemption. |  | Failed_unable to proceed with DD payment alone | Bug | To be taken up for dev | High
156 | 2020-06-12 |  | ECF | How can we proces the ECF if the comodity is multiple in single invoice | Gayathri | This is an exceptional scenario. Claim can be sent for major commodity approver | Not required | Not required
157 | 2020-06-15 |  | AP Invoice maker | Descripton Request for HSN to select the correct HSN code based on the invoice. | Gayathri | Not required | Not required | Not required
158 | 2020-06-15 |  | Inward | Invoice Summary Screen _ able to attach only one document and not able to view the same in maker screen_ since the document is not able to view in UAT | Gayathri | Multiple attachment option available -choose all files at one short with control key, deletion is possible | Clarified | Not required
159 | 2020-06-15 |  | AP Invoice maker | Request to remove (or) add the additional document option in invoice summary maker screen | Gayathri | AP screen invoice maker attachment option should be given | Not required | Not required |  |  | Maruthi | enhancement
160 | 2020-06-15 |  | AP Invoice maker | Unable to capture the Tax type in credit screen , since the vendor maintained TDS. S S ENTERPRISES PAN AJPI5327F2 | Gayathri | Its working now. Problem could be due to loading issue | Clarified | Not required
161 | 2020-06-15 |  | AP Invoice maker | Tax Type is not shown in AP screen at any any level | Gayathri | Sytem loading issue | Clarified | Not required
162 | 2020-06-15 |  | AP Invoice maker | Action disable in Maker Screen for multiple debit line for CCBS Split , as well system should not allow to create a same CCBS at multiple time for the same entry. | Sankari | Bug to be fixed | Bug fixed | Not required |  | 2020-06-21 | Bug | 25h EOD | 2020-06-28
163 | 2020-06-15 |  | AP Invoice maker | In the Payment Screen SUS GL request for passing rectifaction entry | Gayathri | To check with Maruthi if credit GL option is same as this | Clarified | Not required |  |  | Maruthi | multiple GL credit option will be available
164 | 2020-06-15 |  | AP Invoice maker/ECF | System allows the duplicate entry for the same vndor and does not shown the duplicate entry details while dedupe check | Gayathri | Dedup check in ECF to be enhanced- | Bug fixed | Not required |  | 2020-06-21 | Bug | 26th EOD | 2020-07-07
165 | 2020-06-15 |  | AP Invoice maker | GST tab allows to edit the amount in the credit tab at maker level.-AP | Sankari | IF HSN is selected system should not allow to edit GST amount field. | Bug fixed | Not required |  | Next Phase | Bug | 25th EOD | 2020-06-28
166 | 2020-06-15 |  | ECF | ECF resend option Request from the approver end to attach any approval. | Gayathri | To check with Maruthi for implementation | Duplicate | Not required |  | Next Phase | Maruthi | reprocess option can be given- 5th July
167 | 2020-06-15 |  | AP Invoice maker | Petty Expesnes category is not clasified for example , postage, conveyance , pooja. | Vimala | Clarified | Clarified | Not required |  |  | NA
168 | 2020-06-15 |  | AP Invoice maker | Clarification Request for TDS threshold amount _ in Maker screen | Vimala | No threshold maintained now. TDS deducted for all applicable payments | Not required | Not required |  |  | NA
169 | 2020-06-15 |  | Supplier management | In supplier creation _ unable to decrease the branch code | Vimala | To be checked-able to increase branch count not able to decrease | Bug fixed | Not required |  |  | Testing team |  | 2020-07-02
170 | 2020-06-15 |  | ALL Screen | System does not allow the decimal value for Invoice taxable amount-Invoice base amount | Vimala | To check with Maruthi -currently many invoices are received with decimals in taxable amount | Bug fixed | Not required |  |  | Bug | to be pushed from SIT | 2020-06-28
171 | 2020-06-15 |  | ECF | System allows the ECF if the taxable amount is greater than the invoice value | Gayathri | Bug to be fixed | Bug fixed | Not required |  | 2020-06-21 | Bug | 25h EOD | 2020-06-28
172 | 2020-06-15 |  | ECF | How can we proces the ECF if the comodity is multiple in single invoice | Gayathri | pls refer to point 2 | Duplicate | Not required
173 | 2020-06-16 |  | Payment | Resend Option Request from prepare for payment to Audit screen, PPX2006160001 | Gayathri | Not required | Not required | Not required |  |  | NA
174 | 2020-06-16 |  | AP Invoice maker | EDIT Option request for debit line details | Gayathri | Working fine | Clarified | Not required |  |  | NA
175 | 2020-06-16 |  | AP Invoice maker | The system does not shown the debit value once alternate the debit line in maker screen while cross check. Again we have input the same details and through the claim to checker, but in the checker screen debit line value is null. | Gayathri | Working fine | Clarified | Not required |  |  | NA
176 | 2020-06-16 |  | AP Invoice maker | Without debit line entry the system allow to move for the authorise payment too. NPO2006160018 | Gayathri | Working fine | Clarified | Not required |  |  | NA
177 | 2020-06-16 |  | ECF | clarification Request for GST Entry (if raiser missed out the details how can we process in maker level) | Gayathri | option available in AP | Clarified | Not required |  |  | NA
178 | 2020-06-17 |  | AP Invoice maker | GST Key In Purpose | Gayathri | Explained | Clarified | Not required |  |  | NA
179 | 2020-06-19 |  | AP Invoice maker | Clarification Request for DD payment (how we select the Bank account to issue a DD)-asking for IFSC details | Gayathri | To be discussed with Maruthi | Bug fixed | Not required |  |  | Bug | 25h EOD | 2020-07-02
180 | 2020-06-19 |  | AP Invoice maker | System does not support to go for the next screen if HSN is not maintianed or NA as per the invoice, system hanging | Gayathri | HSN to be added in the master | Clarified | Not required
181 | 2020-06-19 |  | AP Invoice maker | HSN Code 8503 | Gayathri |  | Clarified | Not required
182 | 2020-06-19 |  | ECF | System Allows to submit the ECF claim without account details for NEFT however the same is getting struck at AP final approval level only. | Sudhakar | To be discussed with Maruthi | Bug fixed | Not required |  |  | Bug | Since NEFT ac is NA it is allowing. NA to be inactive | 2020-06-28
183 | 2020-06-19 |  | ECF | In Imprest Employee - System allows to submit ECF claim by selecting Credit GL instead of Reimbursement account and the same is getting processed at AP also. | Sudhakar | To be discussed with Maruthi | Bug fixed | Not required |  |  | Bug | 26th EOD | 2020-07-02
184 | 2020-06-19 |  | Supplier management | Supplier Management Modification: Unable to add bank branch details in Payment detail screen.-MICR code to be non mandatory | Sudhakar | To check with Maruthi regarding MICR code | Bug fixed | Not required |  |  | Bug | 25h EOD | 2020-06-28
185 | 2020-06-19 |  | Payment | Payment Details: Unable to provide space between the beneficiary name.same problem in contact details as well | Sudhakar | Bug to be fixed | Bug fixed | Not required |  |  | Bug | 26th OED | 2020-06-28
186 | 2020-06-19 |  | ECF | ECF - Unable to update decimal value in ECF Amount tab. | Sudhakar | Available in SIT and will check in Pre-Prod again | Bug fixed | Not required |  |  |  |  | 2020-06-28
187 | 2020-06-19 |  | ECF | In ECF Inventory screen, changing of approver name is not allowed, we need this to be change as if we want to change approver from one to another for some valid reasons. | Vimala | To be recheck by testing team | Clarified | Not required
188 | 2020-06-19 |  | ALL Screen | search option should be search in all pages whereas now, it searches only at the current page-page count | Vimala | Bug to be fixed | Bug fixed | Not required |  |  | Bug | check and fix | 2020-06-28
189 | 2020-06-19 |  | ALL Screen | Remove attachment option not there, only add attachment option available | Vimala |  | Clarified | Not required
190 | 2020-06-20 |  | Supplier management | If a vendor exceeds actual spend, how can we process the payment | Vimala | approval should be taken from | Clarified | Not required |  |  | Maruthi
191 | 2020-06-20 |  | AP Invoice maker | Is credit GL will be default for all vendors or do we need to create as other payment modes like Neft , DD etc.. | Vimala | doubt cleared | Clarified | Not required
192 | 2020-06-20 |  | Supplier management | for unreg vendor, PAN ,The Tax details should not be Mandatory-system should allow to enter tax details even if PAN is not available | Vimala | Yet to be fixed in preprod | Bug fixed | Not required |  |  |  |  | 2020-06-28
193 | 2020-06-20 |  | ALL Screen | Transaction history should be enabled- need from raiser end | Vimala | to be check | Bug fixed | Not required |  |  | Bug | 26th EOD | 2020-07-02
194 | 2020-06-20 |  | Supplier management | if a vendor having more than 1 branch in same state, then system should allows to enter same GST/tax details for other branches also | Vimala | different branches in same state to be maintained with same GST | Bug fixed | Not required |  |  | Maruthi | Monthend | 2020-06-28
195 | 2020-06-20 |  | Supplier management | NEFT -bank ac no alpha numeric is required- not able to to maintain alpha in wisefin- min 26 chargacters |  | Bug to be fixed | Bug fixed | Not required |  |  | Bug | 25h EOD | 2020-06-28
196 | 2020-06-22 |  | ECF | System allows to select the single entry for multiple User for various type of expenses | Karthik |  | Bug fixed | Not required |  |  | Bug | Monthend | 2020-06-28
197 | 2020-06-22 |  | ECF | System shown the NEFT paymode for branch petty cash EXP.. Pls clarify | Karthik |  | Bug fixed | Not required |  |  | Bug | 26th EOD | 2020-07-02
198 | 2020-06-15 |  | Maintenance | Debit Line upload request | Gayathri |  | Not required | Not required
199 | 2020-06-15 |  | Maintenance | Catalog details should be seperate frame for Product and Service i-e for service also, the UOM, Unit price fields are mandatory | vimala |  | Not required | Not required
200 | 2020-06-23 |  | AP Invoice maker | Variance in taxable amount between ECF and AP | Deen |  | Bug fixed | Not required |  |  |  | 26th EOD | 2020-07-02
201 | 2020-06-23 |  | AP Invoice maker | In AP GL account number for few CAT and SUB Cat is same. When we try to change the Sub cat GL account doesn’t get changed. | Preprod | Clarified | Clarified | Not required
202 | 2020-06-24 |  | Maintenance | Unable to create Delmat limit for the users | Preprod | Need to enter the full name of the employee | Bug fixed | Not required |  |  |  | 26th EOD | 2020-06-28
203 | 2020-06-24 |  | Payment | Prepare Payment - In case of netting, if the vendor name has selected by using filter option, system filtering the vendor only from the first page and not from the other pages. | Preprod | rows to be changed from 10 to 500 | Bug fixed | Not required |  |  |  | 27th EOD | 2020-06-28
204 | 2020-06-24 |  | AP Invoice maker | AP Invoice summary - System allows to edit the GST number of the vendor at Inward level. | Preprod | To be discussed with Maruthi | Bug fixed | Not required |  |  |  | 27th EOD | 2020-06-28
205 | 2020-06-24 |  | Payment | Prepare Payment - System allows to transfer the amount which is greater than the invoice amount | Preprod | Working Fine | Clarified | Not required
206 | 2020-06-24 |  | ECF | Remakrs to be changed as purpose-not allowing special characters | Testing team | Bug to be fixed | Bug fixed | Not required |  |  |  | 27th EOD | 2020-06-28
207 | 2020-06-24 |  | Supplier management | Unable to mark vendor as inactive in supplier mgmt-error in header level | Testing team | Bug to be fixed | Bug fixed | Not required |  |  |  | 27th EOD | 2020-06-28
208 | 2020-06-25 |  | Supplier management | Supplier Branch - Unable to provide space in "Supplier Branch Remarks" column, contact detais=ls etc | Preprod | Bug | Bug fixed | Not required |  |  |  |  | 2020-07-02
209 | 2020-06-25 |  | ECF | ECF - While processing the request along with TDS and TDS exemption, system throws an error as "Some Values Null in Json Data" | Preprod | Bug | Bug fixed | Not required |  |  |  |  | 2020-06-28
210 | 2020-06-25 |  | AP Invoice maker | AP - Payment processed with the invoice contains both Product and Service, TDS is applicable for the service alone. Hence in credit tab, amount of service has entered as taxable amount. However system automatically changing the taxable amount at header level. Hence unable to process... | Preprod | Bug-similar to prepaid shown by Deen | Bug fixed | Not required |  |  |  |  | 2020-07-02
211 | 2020-06-25 |  | ECF | Prepaid Advance - Fields getting ammended on mouse clicking | Preprod | To be discussed with Maruthi | Bug fixed | Not required |  |  |  |  | 2020-06-28
212 | 2020-06-25 |  | AP Invoice maker | Invoice amount are editable at AP level | Preprod | ecf inviice amount in AP not to be edited | Bug fixed | Not required |  |  |  |  | 2020-06-28
213 | 2020-06-26 |  | Inward | Inward - Duplicate entry flows if we click the submit button twice. | preprod | To be discussed with Maruthi | Bug fixed | Not required |  |  |  |  | 2020-06-28
214 | 2020-06-26 |  | ALL Screen | GST key in option in AP audit maker screen - currently available for manual ECF-should be there for all claims | Testing team |  | Bug fixed | Not required |  |  |  |  | 2020-07-02
215 | 2020-06-27 |  | AP Checker | AP Checker - For imprest payments, system automatically picks the hsn code as 1 for GST not applicable cases. | Preprod | Bug | Bug fixed | Not required |  |  |  |  | 2020-07-07
216 | 2020-06-27 |  | AP approval summary | AP Approval Summary - Filter option is not working proper. | Preprod | No Issues | Clarified | Not required
217 | 2020-06-27 |  | ECF | The screen moves to inventroy from AP maker while closing the ECF claim from Raiser end | Preprod | Bug-screen navigates from ECF raiser to AP maker | Bug fixed | Not required |  |  |  |  | 2020-07-07
218 | 2020-06-27 |  | Supplier management | Same account details are able to map for the different vendor | Preprod | No Issues | Clarified | Not required
219 | 2020-06-27 |  | Payment | Prepare payment Netting Option _clarification Request | Preprod | Payment advise is not enabled | Not required | Not required
220 | 2020-06-29 |  | AP Invoice maker | Able to Pick the tax type but rate is not auto populated | Preprod | No Issues | Clarified | Not required
221 | 2020-06-29 |  | Supplier management | Supplier Management - While creating new vendor, Create supplier screen (1st Page) alone enabled and the other tabs are freezed. If we comeout from the screen and reentered, then all the fields are enabled. | Preprod | Bug | Bug fixed | Not required |  |  |  |  | 2020-07-02
222 | 2020-06-29 |  | Supplier management | Supplier Management - While re-entering, details already entered in "Profile Basic" tabs are disappeared. | Preprod | Bug | Bug fixed | Not required |  |  |  |  | 2020-07-02
223 | 2020-06-29 |  | Supplier management | In Supplier branch - System doesn't allows to leave space in "Supplier Branch Name", "Supplier Branch Details", "Activity Name", "Activity Description", Activity Detail Name" | Preprod | Bug | Bug fixed | Not required |  |  |  |  | 2020-07-02
224 | 2020-06-29 |  | AP Invoice maker | AP - Unable to process the request which contains both Product and Service related invoices. | Preprod | Will workfine if TDS part removed from ECF Inventory | Clarified | Not required
225 | 2020-06-29 |  | AP Invoice maker | AP _ unable to process the ECF with discount and other deductions-discount not working | Preprod | To be discussed with Maruthi | Bug fixed | Not required |  |  |  |  | 2020-07-02
226 | 2020-06-29 |  | Supplier management | Supplier Management - While modifying, system allows to save the vendor without any "Paymode". | Testing Team | Bug | Bug fixed | Not required |  |  |  |  | 2020-07-02
227 | 2020-06-29 |  | ECF | ECF - Vendor created without Paymode. Entry created in ECF for this vendor, Since there is not NEFT details system automatically picks BRA account as Paymode…. | Testing Team | Bug | Bug fixed | Not required |  |  |  |  | 2020-07-02
228 | 2020-06-29 |  | AP Invoice maker | RCM - Invoice debit credit validation should not done based on taxable amount | Testing Team | Bug | Bug fixed | Not required |  |  |  |  | 2020-07-02
229 | 2020-06-29 |  | AP Invoice maker | RCM - flag to be triggered basis GL and not through GST no(vendors need not maintain GST for RCM) | Testing Team | Bug | Bug fixed | Not required |  |  |  |  | 2020-07-02
230 | 2020-06-29 |  | ECF | ECF - For the vendor, paymode changed from NEFT and updated as DD, however while raising claims in ECF system shows the NEFT details instead of DD | Testing Team | Bug | Bug fixed | Not required |  |  |  |  | 2020-07-02
231 | 2020-06-29 |  | AP Invoice maker | Invoice Maker - Backward button navigation error | Testing Team | Bug | Bug fixed | Not required |  |  |  |  | 2020-07-02
232 | 2020-06-27 |  | Rent / Property Summary | Choose files option and viewing of the same to be made proper | Aishwarya |  | Bug fixed | Not required |  |  |  |  | 2020-07-07
233 | 2020-06-27 |  | Rent / Expense Create | Date format in the field and calendar to be in sync, currently if we type in the recurring date field (dd-mm-yyy) the calendar in drop down shows mm-dd-yyyy format. And it is better to watermark the format in that field to avoid confusion | Aishwarya |  | Bug fixed | Not required |  |  |  |  | 2020-07-07
234 | 2020-06-27 |  | Rent / Expense Create | The view tab actually allows to edit but instead of editing it actually creates a new recurring | Aishwarya |  | Bug fixed | Not required |  |  |  |  | 2020-07-07
235 | 2020-06-27 |  | Rent / Approval Summary | Expense Type and Type field of search not working | Aishwarya |  | Bug fixed | Not required |  |  |  |  | 2020-07-07
236 | 2020-06-27 |  | Rent / Approval Summary | RUN option to be taken off | Aishwarya |  | Bug fixed | Not required |  |  |  |  | 2020-07-07
237 | 2020-06-27 |  | Rent / Expense GRN Approval | For unregistered, uploading of invoice should not be made mandatory. The same should be followed ven in AP | Aishwarya |  | Bug fixed | Not required |  |  |  |  | 2020-07-07
238 | 2020-06-27 |  | Rent / Expense GRN Approval | The GST calculation made is to be checked once again in this screen | Aishwarya |  | Bug fixed | Not required |  |  |  |  | 2020-07-07
239 | 2020-06-30 |  | ECF | Validation Request for IMPREST in Supplier Payment. |  | Need to check | Bug fixed | Not required |  |  |  |  | 2020-07-02
240 | 2020-06-30 |  | ECF | ECF / AP - System allows to submit the entry without bank details (Bank Name, IFSC Code, etc.). Entry moved to Prepare payment screen....NPO2006300016. |  | To be recheck | Clarified | Not required
241 | 2020-06-30 |  | Inward | AP Invoice Summary - Loading issue.....Once the entry submitted, system shows the screen as Loading and the page is not getting refresh. |  | Check with Selva | Clarified | Not required
242 | 2020-06-30 |  | ECF | ECF / AP - Unable to process the request along with TDS Exemption. |  | Bug | Bug fixed | Not required |  |  |  |  | 2020-07-02
243 | 2020-06-30 |  | ECF | ECF / AP - While creating vendor...tax rate selected as 2%, however in ECF system shows 3 different tax rates for the same TDS Section. |  | TDS Rates pulled from Tax Master | Clarified | Not required
244 | 2020-07-23 |  | FA / PO Template | PO Template: Is not updated (Incl barcode) | FA |  | Bug fixed | Not required |  |  |  |  | 2020-07-07
245 | 2020-07-03 |  | ECF | ECF image, amount in words, purpose not caputured -ECF remarks to be replaced with purpose text | Testing team |  | Bug fixed | Not required |  |  |  |  | 2020-07-07
246 | 2020-07-03 |  | Supplier management | Supplier name field - alllow special characters like -.() etc | Testing team |  | Bug fixed | Not required |  |  |  |  | 2020-07-07
247 | 2020-07-03 |  | Inward | file attachment need not be mandatory in inward screen | Testing team |  | Bug fixed | Not required |  |  |  |  | 2020-07-07
248 | 2020-07-03 |  | Employee query | Accounting entry: serial number continuity changing in 2nd page | Testing team |  | Bug fixed | Not required |  |  |  |  | 2020-07-07
249 | 2020-07-03 |  | Bounce/AP maker | Bounce: The attached file missing in the AP maker screen. | Testing team |  | Bug fixed | Not required |  |  |  |  | 2020-07-07
250 | 2020-07-03 |  | ECF | Invoice maker: HSN% not updating properly in the system, however, while choosing it again its working fine. | Testing team |  | Bug fixed | Not required |  |  |  |  | 2020-07-07
251 | 2020-07-03 |  | ECF | ECF approval: HSN number mismatching, (Note: Selected HSN numbers showing correctly in AP invoice maker and checker) | Testing team |  | Bug fixed | Not required |  |  |  |  | 2020-07-07
252 | 2020-07-03 |  | AP/Audit Maker | Many TDS listed in the drop-down which is not mapped in Vendor management, but AP not showing the tax rates for the unselected TDS maintained in Vendor Master | Testing team |  | Bug fixed | Not required |  |  |  |  | 2020-07-07
253 | 2020-07-04 |  | AP Invoice maker | In AP debit screen FA GL to be maintained if we click capitalize button | Testing team |  | Duplicate | Not required
254 | 2020-07-04 |  | Asset capitalization | Entries are duplicated for capitalization, Location empty, unable to capitalize given amount, error in paid and invoice amount | Testing team |  | Bug fixed | Not required |  |  |  |  | 2020-07-07
255 | 2020-07-04 |  | Maintenance | Paymode DD-maintain GL 275300110 | Testing team |  | Duplicate | Not required
256 | 2020-07-04 |  | Maintenance | Paymode Credit GL- maintain GL275300110 |  |  | Duplicate | Not required
257 | 2020-07-11 |  | ECF/AP | PPX field name and mode name to be changed as "Advance" in all screens | KVB req |  | Duplicate | Not required
258 | 2020-07-30 | PO | PO | PO should have only the base amount of the asset irrespective of HSN/SAC avlb or not | KVB req |  | Enhancement | To be taken up for dev | High
259 | 2020-07-30 |  | PO/AP | Partial payment made against a single PO, the remaining amount/qty should be shown | KVB req |  | Enhancement | To be discussed
260 | 2020-07-30 | FA | FA | F&F payments: Require to view/download F&F report based on the date/month/year selected (i.e for payments made debiting F&F GLs). | KVB req |  | Report | To be taken up for dev | Medium
261 | 2020-07-30 | PO | PO | Configuration details of the hardware/software should be shown in the Purchase Order. | KVB req |  | Enhancement | To be taken up for dev | High